## DESCRIPTION
Project name: Mayer
Description
Đây là một trang web hỗ trợ chúng ta tạo dữ liệu mẫu thuận tiện cho việc lập trình, tương tự như trang web: Mockaroo (https://www.mockaroo.com/). Trang web sẽ gồm các trang chính sau đây: - Schema: trang dùng để xây dụng các bảng quan hệ trong cơ sở dữ liệu của bạn. Một bảng quan hệ ( trong trang web được gọi là SCHEMA) sẽ bao gồm các trường ( gọi là các FIELD). Các field này sẽ có tên, loại dữ liệu, một số yêu cầu yêu. - Dataset: Từ các định nghĩa về các Schema đã được chúng ta tạo ở trên, ta có thể tạo ra các dữ liệu mẫu (trong trang web gọi là DATASET). Các dataset này sẽ được hỗ trợ tải xuống để chúng ta import vào cơ sở dữ liệu mà chúng ta cần. - Project: Tổng hợp các Schema sẽ tạo thành một database, trong trang web sẽ gọi là PROJECT. Trang PROJECT sẽ có nhiệm vụ gom các schema thành một nhóm. - Mock API: Chúng ta có thể test API của các schema này bằng các tạo ra các API. Trang web giúp hỗ trợ test các API đơn giản, ví dụ như GET, POST, PUT, DELETE. - Ngoài ra, trang web có thêm một trang dùng để quản lý tài khoản người dùng với chức năng chẳng hạn thay đổi mật khẩu. - Vì các dữ liệu mẫu được tạo ra từ DATASET là không cố định và tuỳ thuộc vào mỗi Schema mà chúng ta tạo ra nên để dể dàng cho việc đọc và lưu trữ, chúng ta sẽ sử dụng non-database (MongoDB). Còn mô hình dữ liệu quan hệ chính thì ta sẽ sử dụng MySQL để lưu trữ.
Table: Accounts
Table Account sẽ lưu trữ các dữ liệu của người dùng trang web.
Name | Type | Description
id | INT | ID của account
email | VARCHAR | Email mà người dùng sử dụng để đăng nhập vào trang web
password | VARCHAR | Password mà người dùng sử dụng để đăng nhập vào trang web
inserted_at | TIMESTAMP | Thời gian tạo trường dữ liệu
updated_at | TIMESTAMP | Thời gian khi sửa đổi dữ liệu trong trường dữ liệu
Table: Projects
Table Project sẽ lưu trữ các database của người dùng đã tạo, trong các project sẽ quản lý các schema, dataset, api của project đã tạo
Name | Type | Description
id | INT | ID của project
account_id | INT | ID của Account để biết được project thuộc vào Account nào
name | VARCHAR | Tên của Project đã tạo
api_key | VARCHAR
inserted_at | TIMESTAMP | Thời gian tạo trường dữ liệu
updated_at | TIMESTAMP | Thời gian khi sửa đổi dữ liệu trong trường dữ liệu
Table: Schemas
Table Schemas sẽ lưu trữ các table mà người dùng đã tạo ra
Name | Type | Description
id | INT | ID của schema
project_id | INT | ID của Project để biết được schema thuộc vào Project nào
account_id | INT | ID của Acouunt để biết được schema thuộc vào Account nào
name | VARCHAR | Tên của Schemas
inserted_at | TIMESTAMP | Thời gian tạo trường dữ liệu
updated_at | TIMESTAMP | Thời gian khi sửa đổi dữ liệu trong trường dữ liệu
Table: Fields
Table Field sẽ lưu trữ các field của các Schemas
Name | Type | Description
id | INT | ID của field
schema_id | INT | ID của Schema để biết được field thuộc Schema nào
name | VARCHAR | Tên của Field
null_percentage | INT | Phần trăm của lượng dữ liệu đươc tạo ra, ví dụ ta tạo ra 100 cột, nếu null_percentage 50 thì dữ liệu trong dataset trong field này sẽ chỉ tạp ra trong 5 dòng.
type | VARCHAR | Loại của dữ liệu của Field, ví dụ: Name, Birthday, City, ....
data | TEXT | Các cấu hình thêm vào của Field, ví dụ: field là một mảng dữ liệu đặc biệt do người dùng nhập, ...
formula | TEXT
inserted_at | TIMESTAMP | Thời gian tạo trường dữ liệu
updated_at | TIMESTAMP | Thời gian khi sửa đổi dữ liệu trong trường dữ liệu
Table: Apis
Table sẽ lưu trữ các API do người dùng tạo ra.
Name | Type | Description
id | INT | ID của API
account_id | INT | ID của Account để biết được api do Account nào tạo ra
schema_id | INT | ID của Schema để biết được api thuộc Schema nào
name | VARCHAR | Tên của API
method | INT | Phương thực thực hiện của API. 0 tương đương GET, 1 tương đương POST, 2 tương đương PUT, 3 tương đương DELETE
path | VARCHAR | Phần path của API
inserted_at | TIMESTAMP | Thời gian tạo trường dữ liệu
updated_at | TIMESTAMP | Thời gian khi sửa đổi dữ liệu trong trường dữ liệu
Table: Dataset
Table sẽ lưu trữ các mô tả về dataset được tạo ra.
Name | Type | Description
id | INT | ID của Dataset
account_id | INT | ID của Account để biết được dataset do Account nào tạo ra
schema_id | INT | ID của Schema để biết được dataset thuộc Schema nào
name | VARCHAR | Tên của Dataset
collecttion_name | VARCHAR | Tên của key dữ liệu được lưu trữ trong MongoDB
inserted_at | TIMESTAMP | Thời gian tạo trường dữ liệu
updated_at | TIMESTAMP | Thời gian khi sửa đổi dữ liệu trong trường dữ liệu

## TIMER
Project name: Mayer
| Start time: 01/06/2022 | Estimate time (dates) |  | Status Project: | Unfinished
| End time: 31/09/2022 | 59.25 |  |  |  | Status
On-going
To do
| Technology |  |  |  |  | Reported
| Framework |  | ReactJS, Elixir/Phoenix |  |  | Completed
| Database Management System |  | MySQL, MongoDB
Library
| Source code |  | https://github.com/conglam123/mayer
Rule
| Đặt tên folder |  | chữ thường gạch dưới _ | https://www.robinwieruch.de/javascript-naming-conventions/
| Đặt tên biến |  | camelCase
| Đặt tên Component |  | PascalCase
| Đặt tên method |  | camelCase
| Đặt tên file |  | chữ thường gạch dưới _
Frontend
Backend
SST | Task Name |  | Description | Estimated Time (hour) | Status
Initial
1 | Create ERD | Backend |  | 16 | Reported
2 | Template for website | Frontend | The template of the website will be based on https://www.mockaroo.com/ , then analyze the good points and the things that need to be changed to fit the topic | 8 | Reported
3 | Build project structure | Backend |  | 8 | Reported
4 | Creat database | Backend |  | 8 | Reported
5 | Create header, footer and skeleton for website | Frontend |  | 16 | Reported
Register
6 | Implement API for register | Backend | POST: /api/v1/sign_up | 8 | Reported
7 | Create register page | Frontend |  | 8 | Reported
Login
8 | Implement API for login, logout | Backend | POST: /api/v1/sign_in | 8 | Reported
10 | Implement function login by google account | Backend | Use ueberAuth for this function | 8 | To do
11 | Create login page | Frontend | - Layout login by account - Button login by google - Button login by github | 8 | Reported
Project Page
12 | Implement API get List Project | Backend | GET: /api/v1/projects | 8 | Reported
13 | Implement API delete Project | Backend | DELETE: /api/v1/projects | 8 | Reported
14 | Implement function create Project | Backend | POST: /api/v1/projects | 8 | Reported
15 | Implement API update Project | Backend | PUT: /api/v1/projects/:id | 4 | Reported
16 | Display list project | Frontend | - Table project (name, name_file,last modify, ...) - Edit field Name Project - Button delete project - Button delete all project - Button create project | 8 | Reported
17 | Implement API get Project | Backend | GET: /api/v1/projects/:id | 4 | Reported
Schema Page
19 | Implement function add schemas to project | Backend | POST: /api/v1/project/schema | 8 | Reported
20 | Implement API create new schema | Backend | POST: /api/v1/schema | 4 | Reported
21 | Implement API get List Schema | Backend | GET: /api/v1/schema | 4 | Reported
22 | Implement API delete Schema | Backend | DELETE: /api/v1/schema | 4 | Reported
23 | Implement API update Name of Schema | Backend | PUT: /api/v1/schema/:id | 4 | Reported
24 | Display list schemas | Frontend | - Table schemas (name, last modify, ...) - Button delete schema - Button delete all schemas - Button create schema | 8 | Reported
25 | Create new schema page | Frontend | - Text filed name of schema - Button ADD FIELD - Edit field name - Button TYPE OF FIELD - Button FORMULA - Button DOWNLOAD DATA - Button CREATE DATA - Button PREVIEW - Buton SAVE SCHEMA - Button BACK UP SCHEMA - A few extra attributes | 24 | Reported
26 | Implement API for field of schema | Backend | GET: /api/v1/field POST: /api/v1/field DELETE: /api/v1/field/:id PUT: /api/v1/field/:id GET: /api/v1/field/:id | 20 | Reported
27 | Create feature type of column | Frontend | - Search type field - Display type of fields - Filter | 16 | On-going
28 | Implement API get Detail Schema | Backend | GET: /api/v1/schema/:id | 4 | Completed
29 | Implement API update Detail Schema | Backend | PUT: /api/v1/schema/:id | 4 | Completed
30 | Create detail schema page | Frontend | - Layout similar to create schema - Implement a function display this schema - Feature change API Key | 12 | On-going
31 | Implement method preview dataset | Backend |  | 16 | Completed
Dataset Page
32 | Implement function create dataset from schema | Backend | POST: /api/v1/project/dataset | 8 | Completed
33 | Implement API get List Dataset | Backend | GET: /api/v1/dataset | 4 | Completed
34 | Implement API delete Dataset | Backend | DELETE: /api/v1/dataset | 4 | Completed
35 | Display list dataset | Frontend | - Table dataset (name, name_file,last modify, ...) - Button delete dataset - Button delete all dataset - Button create dataset | 8 | On-going
36 | Implement API get Dateset | Backend | GET: /api/v1/dataset/:id | 4 | Completed
37 | Implement API update Name of Dataset | Backend | PUT: /api/v1/dataset/:id | 4 | Completed
39 | Create detail dataset page | Frontend | - Edit field Dataset Name - Zone preview dataset | 10 | On-going
40 | Implement method download file dataset | Backend | POST: /api/v1/dataset from MongoDB | 16 | Completed
Mock Api Page
44 | Implement function create mockapi from schema | Backend | POST: /api/v1/project/api | 8 | Completed
45 | Implement API get List MockAPIS | Backend | GET: /api/v1/api | 4 | Completed
46 | Implement API delete MockAPIS | Backend | DELETE: /api/v1/api | 4 | Completed
47 | Implement API update Name of MockAPI | Backend | PUT: /api/v1/api/:id | 4 | Completed
48 | Implement method create MockAPIS | Backend | POST: /api/v1/api | 8 | Completed
49 | Display list mock apis | Frontend | - Table APIS (name, link_api, last modify, ...) - Button delete API - Delete all APIS - Button create API | 8 | On-going
18 | Create detail project page | Frontend | - Edit field Project Name - Tab display schemas of project - Tab display dataset of project - Tab display apis of project | 8 | On-going
User Setting
41 | Change password of account | Backend | PUT: /api/v1/account/:id for change password | 4 | On-going
42 | Implement API get Detail Account | Backend | GET: /api/v1/account/:id | 4 | On-going
43 | Create account setting page | Frontend | - Feature Change password | 8 | On-going
A few extra features
50 | Implement function login by github account | Backend | Use elixir_auth_github for this function | 8 | On-going
51 | Implement API get MockAPI | Backend | GET: /api/v1/api/:id | 4 | On-going
52 | Implement CRUD API for links of MockAPI | Backend |  | 32 | On-going
53 | Create detail mock api page | Frontend |  | 8 | On-going
54 | Implementation formula function | Backend |  | 16 | On-going
55 | Create feature formula | Frontend |  | 8 | On-going
56 | Implement function backup schema to file | Backend |  | 8 | On-going
57 | Edit email of account | Backend | PUT: /api/v1/account/:id for change email | 8 | On-going